## Sheet1
Task ID | Task Description | Responsible | Status | Estimated hours remaining (day 0 = initial estimate)
started 04/03/2021
|  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Mijlpaal 1 | bar: 0
1 | Make code ready for new additions | Denzell | 100% | 0: 1; 1: 0
2 | Make code ready for new additions | Bernd | 100% | 0: 1; 1: 0
Mijlpaal 2 | bar: 0
| Implementeer piece | Denzell | 100% | 0: 1; 1: 0
Mijlpaal 3 | bar: 0 to 1
| Implementeer bishop | Bernd | 100% | 0: 1->0.5; 1: 0
| Implementeer rook | Bernd | 100% | 0: 1->0.5; 1: 0
| Implementeer knight | Bernd | 100% | 0: 1->0.5; 1: 0
| Implementeer queen | Bernd | 100% | 0: 1->0.5; 1: 0
Mijlpaal 4 | bar: 0
| Fix board | Denzell | 100% | 0: 3->5; 1: 0
Mijlpaal 5 | bar: 0 to 1
| Fix AI | Denzell | 100% | 0: 3->1; 1: 0
Mijlpaal 6 | bar: 0
| Fix print | Bernd | 100% | 0: 2; 1: 0
| Test win condities | Bernd | 100% | 0: 1; 1: 0
Mijlpaal 7 | bar: 0
| Reimplement enpassent | Denzell | 100% | 0: 1; 1: 1; 2: 0
| Implementeer king | Bernd | 100% | 0: 1; 1: 1; 2: 0
Mijlpaal 8 | bar: 0
| Clean up code | Denzell | 100% | 0: 1; 1: 1; 2: 1; 3: 0
Afgewerkt product | bar: 0
| TOTAAL |  | 100% | 0: 17; 1: 3; 2: 1; 3: 0