## Sheet1
Task ID | Task Description | Responsible | Status | Estimated hours remaining (day 0 = initial estimate)
started 04/03/2021
|  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Mijlpaal 1 | bar: 0
1 | Make code ready for new additions | Denzell | 100% | 0: 1; 1: 0
2 | Make code ready for new additions | Bernd | 100% | 0: 1; 1: 0
Mijlpaal 2 | bar: 0
| Implementeer piece | Denzell | 100% | 0: 1; 1: 0
Mijlpaal 3 | bar: 0 to 1
| Implementeer bishop | Bernd | 0% | bar: 0 to 14
| Implementeer rook | Bernd | 0% | bar: 0 to 14
| Implementeer knight | Bernd | 0% | bar: 0 to 14
| Implementeer queen | Bernd | 0% | bar: 0 to 15
Mijlpaal 6 | bar: 0
| Fix board | Denzell | 0% | 0: 3
Mijlpaal 7 | bar: 0 to 1
| Fix AI | Denzell | 0% | 0: 3
Mijlpaal 8 | bar: 0
| Fix print | Bernd | 0% | 0: 2
| Fix victory | Bernd | 0% | bar: 0 to 1
Mijlpaal 9 | bar: 0
0% | bar: 1
Mijlpaal 10 | bar: 0
0% | bar: 1 to 3
0% | bar: 1 to 3
Afgewerkt product | bar: 0
| TOTAAL |  | 0% | 0: 16